## Sample
Sample Draft Application Timeline
Project: | Montara Academy Phase II application
Grant Round: | Spring 2019
Date | Task | Notes
Early November | Meet with architects and SHF staff
Nov-Dec | Obtain bids from contractors for project work
Dec- Feb | Collect letters of support | 2-5 letters (dated within 2 months of Apr.1)
Feb. 1 | Online application live
Before March. 1 | Submit draft application to SHF for preliminary review
April. 1 | Deadline for online application submission
Potential Letters | Contact | Responsibility
| Susan Stone, City Councilwoman | Molly, School Principal
| Bob Jones, Head of neighboring business | Sarah, Grant Administrator
| Ashley Black, Neighborhood Association | Sarah, Grant Administrator
| Sam Bowles, Historic Denver Executive Director | Sarah, Grant Administrator
| Students | Tom, Fifth Grade Teacher
Application | Narrative Section | Notes
| Applicant Capacity | List past SHF grants and share successes
| Resource Description and Project History | Add paragraph about recent preservation work and planned work
| Scope of Work & Budget | Working with architect and contractor to draft this
| Project Description | Working with architect to draft this
| Project Milestones | Working with architect to draft this
Urgency
Public Benefit
Other | Attachments | Notes
| Existing condition photos | architect will provide photos
Draft Application Timeline
Project:
Grant Round:
Date | Task | Notes
Potential Letters | Contact | Responsibility
Application | Narrative Section | Notes
Other | Attachments | Notes

## Blank
Draft Application Timeline
Project:
Grant Round:
Date | Task | Notes
Potential Letters | Contact | Responsibility
Application | Narrative Section | Notes
Other | Attachments | Notes